## Week 1
Nathan Smith
2021-05-03
Master of Data Science Capstone Project - 2021 |  |  | Week #
University of British Columbia - Okanagan |  |  | 1
Kelowna, BC
CLIENT
Urban Data Labs
DESCRIPTION | Activity Type | HRs
2021-05-03
Start setting up project templates | Project Management | 1
Internal kick-off meeting | Internal Meetings | 0.5
Client kick-off meeting | Client Meetings | 1
Internal post-client meeting | Internal Meetings | 0.5
Discuss and write team-contract.md and initial planning | Internal Meetings | 1
Email client selection of project | Client Communication | 0.75
Start proposal powerpoint | Project Documents | 1
Clubhouse setup, branch protection, merge template PR, Slack workspace | Project Management | 1.5
Previous project review, Gantt chart options | Project Management | 3
10.25
2021-05-04
Templates for meeting minutes, stand-ups, and sprints | Project Management | 1.5
MDS capstone kick-off meeting | UBC Meetings | 2
Work on proposal powerpoint | Project Documents | 0.5
Review links provided by client | Background Review | 1
Setup meeting agenda and sprint plan for meeting next day | Project Management | 0.75
Internal meeting to discuss proposal and next client meeting | Internal Meetings | 0.5
Correspondence with client and setup docs in OneDrive with client | Client Communication | 0.5
Add WorkLog template, transfer logs, PR template branch | Project Management | 0.5
Discuss Gantt chart and tasks | Internal Meetings | 0.5
7.75
2021-05-05
Update Gantt chart and upload to OneDrive for client | Project Documents | 1
Stand-up | Internal Meetings | 0.25
Work on proposal/review progress to date on it | Project Documents | 1
Meeting with client to discuss project | Client Meetings | 0.75
Internal post client meeting | Internal Meetings | 0.5
Update meeting minutes | Client Communication | 0.5
Update Gantt chart | Project Documents | 0.25
Work on proposal statement of work section | Project Documents | 2.25
6.5
2021-05-06
Work on proposal | Project Documents | 2
Stand-up | Internal Meetings | 0.25
Work on proposal | Project Documents | 1.25
Scrum meeting with client | Client Meetings | 0.75
Kanban board organization and scrum meeting document clean-up | Project Management | 0.75
Finish draft proposal | Project Documents | 1.75
6.75
2021-05-07
Update proposal with client comments | Project Documents | 1.5
Stand-up | Internal Meetings | 0.25
Proposal Presentation | Project Documents | 2.5
High-level review of anomaly detection algorithms | Background Review | 1.5
5.75
2021-05-08
Finalize proposal and presentation | Project Documents | 1
Update GitHub READMEs | Project Management | 0.5
1.5
2021-05-09
0
TOTAL |  | 38.5
ADDITIONAL COMMENTS

## Week 2
Nathan Smith
2021-05-10
Master of Data Science Capstone Project - 2021 |  |  | Week #
University of British Columbia - Okanagan |  |  | 2
Kelowna, BC
CLIENT
Urban Data Labs
DESCRIPTION | Activity Type | HRs
2021-05-10
Review InfluxDB docs, run UDL SkySpark example | Understand InfluxDB | 2
Stand-up | Internal Meetings | 0.25
Review InfluxDB docs to understand how streaming architecture would work | Understand InfluxDB | 2.25
Meeting with UDL to discuss InfluxDB/Telegraf | Client Meeting | 1.25
Post-meeting internal discussion | Internal Meetings | 0.5
Write-up meeting minutes | Project Documents | 0.25
Working on getting InfluxDB and Telegraf running locally | Parsing Files | 4.5
11
2021-05-11
Working on getting InfluxDB and Telegraf running locally | Parsing Files | 1.25
Logs and GitHub cleanup | Project Management | 0.25
Research how streaming anomaly detection would work with InfluxDB | InfluxDB Streaming | 0.25
Stand-up and presentation run-through | Internal Meetings | 0.75
Research how streaming anomaly detection would work with InfluxDB | InfluxDB Streaming | 1
Presentation (incl prep before) | UBC Meetings | 0.75
Research how streaming anomaly detection would work with InfluxDB | InfluxDB Streaming | 4.25
8.5
2021-05-12
Figure out and code a simple simulator in Python not reliant on InfluxDB | Streaming Simulation | 2.75
Extended stand-up to discuss where we're each at | Internal Meetings | 0.75
Project file clean-up | Project Management | 0.25
Research how streaming anomaly detection would work with InfluxDB | InfluxDB Streaming | 4
Testing using telegraf reading data from InfluxDB | InfluxDB Streaming | 2
Meeting with Ryan to discuss data parsing | Data parsing | 0.25
10
2021-05-13
Influxdb streaming and parsing | Data parsing and streaming | 2.5
Setup sprint planning doc | Project Management | 0.5
Clean-up streaming research and PR files and discussion | InfluxDB Streaming | 1.5
Stand-up and sprint planning discussion | Internal Meetings | 0.5
Parsing discussions/research | InfluxDB Parsing | 1
Kanban board updates | Project Management | 0.25
Streaming system ppt slides for meeting | Project Management | 0.25
Sprint planning meeting | Meeting with client | 0.75
Post-sprint meeting | Internal Meetings | 0.25
Clean-up meeting minutes and streaming ppt for Jiachen to talk to EWS | Project Documents | 1
Streaming parsing work | InfluxDB Parsing | 1 | 9.5
2021-05-14
Testing various InfluxDB streaming methods | InfluxDB Streaming | 4.75
Stand-up | Internal Meetings | 0.25
Testing various InfluxDB streaming methods | InfluxDB Streaming | 0.25
Dealing with python environment issues | InfluxDB Streaming | 0.5
Work on weekly presentation | Project Documents | 2.75
Upload OneDrive documents to GitHub with updated logs | Project Management | 0.75
Client slack discussions on the parser and meetings Monday | Project Management | 0.25
9.5
2021-05-15
0
2021-05-16
Testing how to query from InfluxDB for model training | InfluxDB Queries | 2
Build derivative docker image for Telegraf with Python installed | InfluxDB Queries | 1
Test continuous Python script call from Telegraf | InfluxDB Queries | 1
Purging tokens from Github | Project Management | 1.5
5.5
TOTAL |  | 54
ADDITIONAL COMMENTS

## Week 3
Nathan Smith
2021-05-17
Master of Data Science Capstone Project - 2021 |  |  | Week #
University of British Columbia - Okanagan |  |  | 3
Kelowna, BC
CLIENT
Urban Data Labs
DESCRIPTION | Activity Type | HRs
2021-05-17
Building code to query InfluxDB records with detection model | InfluxDB Streaming Framework | 1.5
Discuss EDA with Ryan | EDA | 0.25
Setup meeting minutes for client meeting today and update Clubhouse | Project Management | 0.25
Stand-up | Internal Meetings | 0.5
Building code to query InfluxDB records with detection model | InfluxDB Streaming Framework | 2
Meeting with UDL on anomaly detection and streaming methods | Client Meetings | 1
Post client meeting to discuss direction | Internal Meetings | 0.75
Correspondance with UDL on Friday meeting with Technical Safety BC | Project Communication | 0.25
Update meeting minutes | Project Documents | 0.25
Building code to write to InfluxDB records for detection model | InfluxDB Streaming Framework | 2.25 | 9
2021-05-18
Adding code to github after tokens purged from repo | Misc | 1
Going through repo and update all code to use environment variables for tokens | Misc | 1
Stand-up / discussion on PR / go over presentation | Internal Meetings / Code Review | 0.75
Building code to write to InfluxDB records for detection model | InfluxDB Streaming Framework | 1
UBC Prof Meeting | UBC Meeting | 0.75
Discuss anomaly detection algorithms and read paper | Anomaly Detection Research | 1
Parsing InfluxDB line protocol for predict method | InfluxDB Streaming Framework | 4
9.5
2021-05-19
Building code to write to InfluxDB records for detection model | InfluxDB Streaming Framework | 2
Extended stand-up discussion plan/project schedule | Internal Meetings | 1
PR streaming framework code (putting it on hold for now) | InfluxDB Streaming Framework | 0.5
Update docker files related to testing the InfluxDB streaming setup | InfluxDB Streaming Framework | 0.75
Sprint planning doc prep and Clubhouse prep/clean-up | Project Management | 1
Work on week 4 status presentation | Project Documents | 2
Update logs and github | Project Management | 0.25
Review anomaly detection research PR | Anomaly Detection Research | 1
Presentation for Tech Safety BC meeting Friday | Project Documents/Client Meetings | 1.5
Review EDA PR | EDA | 0.5 | 10.5
2021-05-20
Initial research on Grafana to understand dashboard level-of-effort | Dashboard Research | 4
Stand-up | Internal Meetings | 0.5
Sprint planning meeting | Client Meetings | 1
Helping UDL with data streaming parsing | Streaming Parsing support for UDL | 1.25
Discuss anomaly detection approach w/ Ryan and generate schematic | Anomaly Detection Research | 1.25
Document Grafana research (sufficient understanding for now) | Dashboard Research | 1.25
Helping UDL with data streaming parsing | Streaming Parsing support for UDL | 1.5
10.75
2021-05-21
Update PowerPoint for meeting with TechSafety BC | Project Documents | 1
Anomaly detection model discussions | Anomaly Detection Model | 1
Meeting with TechSafetyBC | Client Meetings | 1
Post meeting discussion with UDL and discussionon next steps | Client Meetings / Data Access | 1.25
Go over with Ryan how to start downloading data from SkySpark manually | Data Access | 0.25
Meeting with Scott to discuss proposed method | UBC Meeting / Model Selection | 0.75
Post meeting discussion | Internal Meeting | 0.25
Figuring out a way to easily view and label anomalies | Anomaly Labelling | 3.5
9
2021-05-22
Built a Shiny app to support labelling anomalies | Anomaly Labelling | 8.5
Update Week 4 Status Presentation | Project Documents | 0.5
9
2021-05-23
Anomaly labelling | Anomaly Labelling | 7
7
TOTAL |  | 64.75
ADDITIONAL COMMENTS

## Week 4
Nathan Smith
2021-05-24
Master of Data Science Capstone Project - 2021 |  |  | Week #
University of British Columbia - Okanagan |  |  | 4
Kelowna, BC
CLIENT
Urban Data Labs
DESCRIPTION | Activity Type | HRs
2021-05-24
Update anomaly labelling files | Anomally Labelling | 1
Stand-up / meeting to discuss model building | Internal Meeting | 1
Sketch out anomaly model components and hand-off streaming-frameworks code to Ryan | Build Model | 1
Write email to UDL/EWS on anomaly label questions | Anomally Labelling | 1
Repo clean-up | Project Management | 1.5
Summarize weekly time/tasks (not previously done) | Project Documents/Project Management | 1.5
Update status presentation | Project Documents | 0.5
Discuss model pipeline with Ryan | Model Pipeline | 0.25
Discuss model pipeline with Mitch | Model Pipeline | 0.25
8
2021-05-25
Discuss data access and anomaly labels with UDL | Data Access/Anomally Labelling | 1
Work on mid-project status presentation | Project Documents | 1.75
Stand-up and go over presentation | Internal Meeting | 0.75
PR review for LSTM model | Model Pipeline | 0.75
Meeting with UBC profs | UBC Meetings | 0.75
Post-meeting team discussion | Internal Meeting | 0.25
PR discussion with Mitch | Model Pipeline | 0.5
Preparing variations on labelled data | Anomally Labelling | 1.75
Message UBC Profs on labelled data plan | Anomally Labelling | 0.75
8.25
2021-05-26
Review cleaning pipeline code | Model Pipeline | 1.25
Emailing/messaging UDL/EWS | Anomally Labelling | 0.75
Stand-up | Internal Meeting | 0.25
Get sprint planning doc ready and clean-up Clubhouse | Project Management | 0.5
Work on status presentation | Project Documents | 1.5
Messaging with Jiachen | Client Communication | 0.25
Discussions with Profs/TAs on approach study/modelling | Modelling Approach | 1.25
PR reviews for LSTM model and for cleaning pipeline | Model Pipeline | 0.5
Modelling discussions with Ryan/Mitch | Model Pipeline | 0.75
File structure for model package | Model Pipeline / Project Management | 1 | 8
2021-05-27
Stand-up | Internal Meeting | 0.5
Testing spectral-residual transormations/discuss with TA | Modelling Approach | 3
Sprint planning meeting | Client Meeting | 0.5
Working with Jiachen on streaming parsing | Parsing | 0.5
Post-sprint planning meeting | Internal Meeting | 0.5
Testing spectral-residual transormations/discuss with TA | Modelling Approach | 4
Code discussion with Ryan | Model Pipeline | 0.25
9.25
2021-05-28
Commit various project management docs to github and setup minutes for Monday | Project Management | 0.75
Code discussion with Ryan | Model Pipeline | 0.25
Stand-up | Internal Meeting | 0.5
PR review on model pipeline | Model Pipeline | 0.25
Start report template (waiting on code) and discuss report with Ryan | Final Report | 2
Discuss spectral residual transformation with Debangsha | Modelling Approach | 0.5
Custom transformer class for spectral residual code | Modelling Approach | 1.75
Discuss preliminary model results and results template notebook | Model Results | 0.75
Modelling | Model Results | 3
9.75
2021-05-29
Modelling | Model Results | 4
Researching various LSTM architectures | Modelling Approach | 4.5
8.5
2021-05-30
Researching various LSTM architectures (incl discussion with Ryan) | Modelling Approach | 3
3
TOTAL |  | 54.75
ADDITIONAL COMMENTS